## 1. Instructions
Instructions
This calculator is intended as a time management tool only. Verify all information with you program, advisor, or committee. We welcome feedback to improve this calculator; please contact us at library@uoguelph.ca.
Note: Parts of this document are not locked so that you may more easily edit and adjust to your own needs. Please download or save a copy to edit.
1. This workbook has the following sheets: Instructions, Parts of my thesis, Calculator from Current Date, Timeline from Current Date, Calculator from Completion Date, Timeline from Completion date.
2. Each sheet includes a set of instructions in the A1 cell.
3. This workbook is designed so that each Calculator populates the corresponding Timeline. For example, the data in tab 3a. Calculator from Current Date populates the timeline in tab 3b. Timeline from Current Date.
4. We suggest that you start using this workbook by choosing either tab 3a. Calculator from Current Date or tab 4a. Calculator from Completion.
5. If you want to start from today's date and work forward with the calculator estimating your completion date, choose tab 3a. Calculator from Current Date to begin.
6. If you know the date you want to complete your requirements by, and wish to work backwards from that date, choose tab 4a. Calculator from Completion to begin.
7. Visit tab 5 University of Guelph Resources for information and further support.
8. Microsoft Excel has some accessibility limitations, for more accessible options and ideas, visit:
9. Review how to use a screen reader to explore and navigate excel
10. Review keyboard shortcuts in excel
11. Email lib.a11y@uoguelph.ca if you have any accessability concerns or requests.
End of instructions
This work is licensed by the Univeristy of Guelph CC BY-NC-SA.
Created by Heather Grierson.
Inspired by “Thesis Completion Calculator” by Jodie Salter, University of Guelph.
I acknowledge the original work as an important conceptual influence.

## 2. Parts of my Thesis
Instructions: 1. Starting in cell C6, modify this list to reflect the sections of your thesis. 2. You can list the major sections or separate into subsections. 3. Current content is an example only. 4. In Column D estimate, in weeks, how long you think it will take to write the first draft of each section. 5. Cell D3 will indicate the total number of weeks you have estimated to complete the first draft. 6. Note: This number will automatically populate parts of Tab 3a. Calculator from Current Date. 7. Note: All numbers in column D from D6 onwards will calculate in D3, ensure you are not double counting
Weeks to Complete First Versions for Supervisor
19.5
| # | Edit the titles in Column B as needed. Example provided. | Estimate the number IN WEEKS it will take you to write the first version you send to your supervisor
| 1 | Introduction/Literature Review | -
| 2 | Introduction | 0.5
| 3 | Literature review | -
| 4 | Introduction | 1
| 5 | Body | 3
| 6 | Conclusion | 0.5
| 7 | Chapter 1 or Study 1 | -
| 8 | Introduction | 1
| 9 | Methods | 1
| 10 | Results | 1
| 11 | Discussion | 1
| 12 | Conclusion | 0.5
| 13 | Chapter 2 or Study 2 | -
| 14 | Introduction | 1
| 15 | Methods | 1
| 16 | Results | 1
| 17 | Discussion | 0.5
| 18 | Conclusion | 0.5
| 19 | Chapter 3 or Study 3 | -
| 20 | Introduction | 0.5
| 21 | Methods | 0.5
| 22 | Results | 1
| 23 | Discussion | 0.5
| 24 | Conclusion | 0.5
| 25 | General Discussion | -
| 26 | Overview | 0.5
| 27 | Key Findings | 0.5
| 28 | Future directions | 0.5
| 29 | Conclusions | 0.5
| 30 | References | 0.5
| 31 | Appendices | 0.5
| 32 | Other
| 33 | Other
| 34 | Other
| 35 | Other
| 36 | Other
| 37 | Other

## 3a.Calculator from Current Date
Instructions: 1. Enter dates as instructed in cells D4 and D5 in Section A. Complete cells D10 - D19 in Section B. 2. This calculator will use this information to fill out the rest of Sections C & D. 3. Note: There are tips in cells F9 and F11.
| Section A. Tasks | Today's Date
| 1. Enter today's date in cell B3 (yyyy-mm-dd). | 2025-01-13
| 2. Enter the deadline (yyyy-mm-dd) for submitting your thesis to the Atrium. Check to confirm: https://calendar.uoguelph.ca/graduate-calendar/schedule-dates/ | 2026-03-14
3. Review the statements below and estimate the time in weeks each step will take. The times already listed are guidelines. Use these to inform your estimates. Consider how long it has taken your supervisor and committee members to reply, edit, set meeting times, etc. and if there is a scheduled holiday or break.
4. Review the dates in your thesis completion timeline. When presenting dates to your supervisor or committee members, we recommend adding additional buffer time.
| Section B. Respond to the following statements or questions. | Enter Time in Weeks | Tip: Indicate 0 for any task already completed.
| 1. How many weeks do you estimate that it will take you to complete your data collection? | 8
| 2. For how many weeks will you focus on your data analysis? | 4 | Tip: Writing is an iterative process. We encourage you to write while collecting data, analyzing it, etc. Do not wait for one section or task to be completed before beginning to write about it.
| 3. Estimate the number of weeks you will need to write the initial version or first draft. Note: The calculation in cell D12 comes from tab 2. Parts of my Thesis. To change this you may edit tab 2. Parts of my Thesis or type a number into cell D12 on this sheet. | 19.5
| 4. You will likely submit portions of your work to your supervisor on an ongoing basis and you will need to allot additional time for your supervisor to read and provide comments on your drafts. We recommend allotting at least 1/3 of the writing time to this process. | 6.435
| 5. Your first draft is ready to be submitted to your committee. Allow at least 4 weeks for advisory committee comments and corrections on a first draft to your thesis. Increase the number of weeks if you want or need more time. | 4
| 6. Once the committee has returned your first draft with comments, how many weeks will you need to edit and complete the second draft? | 2
| 7. How many times do you think you go back and forth with your supervisor or committee before completing your final draft? We recommend adding at least 2 weeks for each iteration after the second draft. | 2
| 8. Allow a MINIMUM of 2 weeks for your advisory committee to approve your final draft thesis. Increase the number of weeks if you want or need more time. | 2
| 9. PhD Thesis: Allow 8 weeks for review by the examination committee. Master's Thesis: Edit D18 to allow 4 weeks for review by the examination committee. Note for all: Confirm the number of required weeks with your advisor. | 8
| 10. Assuming a successful defence, how many weeks will you need to complete your corrections after your defence, including Atrium requirements? | 2
| Section C. Your Thesis Completion Timeline | Dates
| Most of your DATA COLLECTION should be finished; you can focus on data analysis. | 2025-03-10
| You have now completed enough ANALYSIS to shift your focus to writing your thesis. | 2025-04-07
| Based on this estimate, you should have a FIRST DRAFT of your thesis to your advisory committee not later than the end of this week: | 2025-10-05 13:05
| Your committee has reviewed your first draft and you have completed the edits. You are now ready to submit your SECOND DRAFT. | 2025-11-16 13:05
| You should have a FINAL DRAFT of your thesis ready to submit to your advisory committee no later than the end of this week: | 2025-11-30 13:05
| The earliest date at which you should expect to have FINAL SIGNOFF FROM YOUR ADVISORY COMMITTEE, an external examiner chosen, and a defence date booked is the end of this week: | 2025-12-14 13:05
| The earliest date at which you should expect to schedule your DEFENCE to allow time for the entire examination committee to review your thesis. Adjust as needed for university closures, committee member holidays, etc. | 2026-02-08 13:05
| Your estimated COMPLETION DATE (date by which thesis is submitted to the Atrium, all other paperwork is complete, all fees are paid, and all accounts are settled) is the end of this week: | 2026-02-22 13:05
| Section D. Number of days between your estimated completion date and date to submit to the atrium. | 19.455
Red/Negative. Your completion estimate is after your atrium deadline. Green/Positive. You have some buffer time. Well done! Note holidays, work already completed, unexpected delays, university closures, etc.
Next: Click the tab 3b. Timeline from Current Date to see the timeline you've just created.

## 3b. Timeline From Current Date
Instructions: 1. The visual timeline which begins at cell B16 can be copied and pasted into presentations or documentation for your advisory committee. 2. Make any changes to dates in Column A only. 3. Make any changes to titles in Column D, rows D5 to D13. 4. Change the height or direction of lines within the timeline by increasing or decreasing the number in column F, cells F5 - F13, Line Height and Direction. Positive numbers will position the event above the timeline. Negative numbers will position the event below the timeline. 5. Directions to create this timeline were found at: https://www.youtube.com/watch?v=619_NoPyba8
| Date (Month-Year) | Date As Text (Month Day) | Events | Date and Events Combined | Line Height & Direction
| 2025-01-06 |  |  |  | 0
| 2025-01-13 | Jan 13 | START DATE | Jan 13 START DATE | 1
| 2025-03-10 | Mar 10 | DATA COLLECTION | Mar 10 DATA COLLECTION | -1
| 2025-04-07 | Apr 7 | ANALYSIS | Apr 7 ANALYSIS | 1
| 2025-10-05 13:05 | Oct 5 | FIRST DRAFT | Oct 5 FIRST DRAFT | -0.5
| 2025-11-16 13:05 | Nov 16 | SECOND DRAFT | Nov 16 SECOND DRAFT | 0.5
| 2025-11-30 13:05 | Nov 30 | FINAL DRAFT TO ADVISORY COMMITTEE | Nov 30 FINAL DRAFT TO ADVISORY COMMITTEE | -1
| 2025-12-14 13:05 | Dec 14 | FINAL COMMITTEE SIGNOFF EXTERNAL EXAMINER CHOSEN DEFENCE DATE SET | Dec 14 FINAL COMMITTEE SIGNOFF EXTERNAL EXAMINER CHOSEN DEFENCE DATE SET | 1
| 2026-02-08 13:05 | Feb 8 | DEFENCE | Feb 8 DEFENCE | -0.5
| 2026-02-22 13:05 | Feb 22 | COMPLETION DATE SUBMISSION TO ATRIUM | Feb 22 COMPLETION DATE SUBMISSION TO ATRIUM | 1
| 2026-03-04 13:05 |  |  |  | 0
Formulas:
Date (Month-Year) = [Date As Text (Month Day), row below]-7

## 4a. Calculator from Completion
Instructions: 1. Fill in cell B4 with your desired completion date. 2. Review the estimated times in cells B10 - B18 and adjust as necessary. 3. Section C will highlight any dates that have passed. 4. Note: Today's date has been automatically selected for you in cell B1. If you do not want it to continue re-setting each time you open it, please remove the formula and type in the date (dd-mon-yyyy). The date is needed for calculations in Section C. 5. Note: There is a tip in cell C9. | 2025-11-27
Section A. Tasks | Completion Date
1. Enter your estimated COMPLETION DATE in cell B4. This is the date at which thesis and application to graduate are submitted in Graduate Program Services and all other paperwork is complete, all fees are paid, and all accounts are settled. Use the date listed here (https://calendar.uoguelph.ca/graduate-calendar/schedule-dates/) for your Atrium Submission or an earlier date of your choice. | 2026-06-08
2. Review the statements in Section B and estimate the time in weeks each step will take. The times already listed are guidelines for you to adapt. Consider how long it has taken you, your supervisor and committee members to reply, edit, set meeting times, etc., and if there is a scheduled holiday or break.
3. Review the dates in Section C. When presenting dates to your supervisor or committee members, consider adding additional time in case your estimates are inaccurate.
Section B. Respond to the following statements or questions. | Enter Time in Weeks | Tip: Indicate 0 for any task already completed.
1. Assuming a successful defence, how many weeks will you need to complete your corrections after your defence, including Atrium requirements? | 2
2. PhD Thesis: Allow eight weeks for review by the examination committee. Master's Thesis: Edit B12 to allow four weeks for review by the examination committee. Note for all: Confirm the number of required weeks with your advisor. | 8
3. How many weeks will you need to exchange additional drafts with your supervisor or committee? We recommend at least two weeks for each iteration after the second draft. | 2
4. After the committee has returned your first draft with comments, how many weeks will you need to edit and complete the second draft? | 2
5. Your first draft is ready to be submitted to your committee. Allow at least 4 weeks for advisory committee comments and corrections on a first draft of your thesis. Increase the number of weeks if you want or need more time. | 4
6. You will likely submit portions of your work to your supervisor on an ongoing basis and you will need to allot additional time for your supervisor to read and provide comments on your draft. We recommend allotting at least 1/3 of the writing time to this process. | 3
7. Estimate the number of weeks you will need to write the initial version or first draft. Note: The calculation in D12 comes from tab 2. Parts of my Thesis. To change this you may edit tab 2. Parts of my Thesis or type a number into cell D12. | 19.5
8. For how many weeks will you focus on your data analysis? | 4
9. How many weeks do you estimate that it will take you to complete your data collection? | 1
Section C. Your Thesis Completion Timeline | Dates | Notes
You need to begin working on your DATA COLLECTION on or before this date. | 2025-07-23 12:00 | This date has passed
Most of your DATA COLLECTION should be finished; you can focus on data analysis. | 2025-07-30 12:00 | This date has passed
You have now completed enough ANALYSIS to shift your focus to writing your thesis. | 2025-08-27 12:00 | This date has passed
Based on this estimate, you should have a FIRST DRAFT of your thesis to your advisory committee not later than the end of this week: | 2026-02-01 | This date is in the future
You should have a FINAL DRAFT of your thesis ready to submit to your advisory committee by the end of this week: | 2026-03-15 | This date is in the future
The latest date at which you should expect to have FINAL SIGNOFF FROM YOUR ADVISORY COMMITTEE, an external examiner chosen, and a defence date booked is the end of this week: | 2026-03-29 | This date is in the future
Request that your DEFENCE DATE be on or before this week. Adjust as needed for university closures, committee member holidays, etc. | 2026-05-24 | This date is in the future
After your defence, begin working on CORRECTIONS. | 2026-05-25 | This date is in the future
This is your COMPLETION DATE (date by which thesis is submitted to the Atrium, all other paperwork is complete, all fees are paid, and all accounts are settled). | 2026-06-08 | This date is in the future
Section D. Evaluating Your Timeline
This timeline is based on the date by which you indicated you want to complete your degree requirements and on the length of time you estimated it would take to complete the work. Consider if there is any work you have left to do that is highlighted as the date having passed (in red). Check tab 4b. Timeline from Completion to see your timeline in graph format.

## 4b. Timeline from Completion
Instructions: 1. The visual timeline which begins at cell B16 can be copied and pasted into presentations or documentation for your advisory committee. 2. We recommend that you make any changes to dates in Column B or Column C only. Columns A and D have formulas attached to other cells. 3. Change the height or direction of lines within the timeline by increasing or decreasing the number in Line Height and Direction. Positive numbers will position the event above the timeline. Negative numbers will position the event below the timeline. 4. Most directions to create this timeline were found at: https://www.youtube.com/watch?v=619_NoPyba8
Date (Month-Year) | Date As Text | Events | Date and Events Combined | Line Height and Direction
2025-07-16 12:00 |  |  |  | 0
2025-07-23 12:00 | Jul 23 | DATA COLLECTION | Jul 23 DATA COLLECTION | -1
2025-07-30 12:00 | Jul 30 | DATA ANALYSIS | Jul 30 DATA ANALYSIS | 1
2025-08-27 12:00 | Aug 27 | WRITING FIRST DRAFT | Aug 27 WRITING FIRST DRAFT | -1
2026-02-01 | Feb 1 | FIRST DRAFT | Feb 1 FIRST DRAFT | 1
2026-03-15 | Mar 15 | FINAL DRAFT TO ADVISORY COMMITTEE | Mar 15 FINAL DRAFT TO ADVISORY COMMITTEE | 1
2026-03-29 | Mar 29 | FINAL COMMITTEE SIGNOFF External examiner chosen Defence date booked by the end of this week | Mar 29 FINAL COMMITTEE SIGNOFF External examiner chosen Defence date booked by the end of this week | -1
2026-05-24 | May 24 | DEFENCE DATE | May 24 DEFENCE DATE | 1
2026-06-08 | Jun 8 | COMPLETION DATE SUBMISSION TO ATRIUM | Jun 8 COMPLETION DATE SUBMISSION TO ATRIUM | -1
2026-06-18 |  |  |  | 0

## 5. Resources
Instructions: Resources are listed in Column A. Corresponding links are in Column B.
University of Guelph Resources | Links
Graduate & Postdoctoral Studies: Completion and Graduation | https://graduatestudies.uoguelph.ca/current/completion
Graduate Calendar | https://www.uoguelph.ca/registrar/calendars/graduate
Atrium Institutional Repository Guide | https://guides.lib.uoguelph.ca/atrium
Library Appointments | https://www.lib.uoguelph.ca/using-library/appointment-booking/
Templates for Atrium Submission | https://graduatestudies.uoguelph.ca/current-students/preparation-your-thesis